## 📋 Cover Page
ContractOS
Enterprise SaaS — System Requirements Document
Construction & Contract Management Platform
Version 1.0 ¦ Confidential ¦ Leadership & Developer Reference
Prepared For | Leadership & Development Team
Document Status | Draft — Pending Final Review
Compliance | PDPA 2010 ¦ ISO 27001 ¦ SOC 2
Target Market | Malaysian Construction Industry
Priority Module | Finance & Invoicing
Currency Support | Multiple Currencies
📂 Document Index
Sheet Name | Description
📋 Cover Page | This sheet — document overview & metadata
🏗️ System Overview | High-level platform summary & build order
📦 Module Requirements | All 13 modules with full requirements
🔄 Project Lifecycle | 6-phase construction workflow (Fasa 1–6)
👥 User Roles & Access | All roles and their access permissions
🔐 Security Requirements | 12 security controls — PDPA & ISO 27001
⚙️ Gap Audit Log | All gaps identified and resolved
💰 Pricing & Subscriptions | Freemium model, tiered plans, billing cycles
🚀 Onboarding Flow | Signup wizard, email verification, guided tour
🔔 Notifications | Channels, customisation & timing
📊 Reports & Analytics | Report types, formats & scheduling
🏢 Multi-Tenancy | Workspace separation, subsidiaries & branding
💳 Payment Gateway | Stripe integration, FPX, auto-renewal
🎨 Branding & Design | Colours, fonts, logo & UI identity
🌐 Landing Page | Sections, CTA, language & content
📧 Email System | Email types, sender config & templates
🔗 Integrations | Accounting, e-signature, WhatsApp, Gov portals
🆘 Support System | Help centre, live chat, AI chatbot
☁️ Hosting & Domain | AWS, server locations & domain

## 🏗️ System Overview
ContractOS — System Overview
🎯 Platform Identity
Property | Value
Platform Name | ContractOS
Product Type | Enterprise SaaS — Web & Mobile PWA
Industry | Construction & Contract Management
Target Users | Solo users, Internal teams & Paying customers
Theme | Dark & Professional (Navy, Black, Grey)
Primary Language | English (Malaysian context)
Currency | Multiple currencies supported
Tax Compliance | Malaysian SST / GST (optional per invoice)
🔨 Build Order
Priority | Component | Description
1 | Landing Page | Public marketing page for visitors
2 | Login & Signup | Secure authentication with optional 2FA
3 | Dashboard | Main app home — role-based views, charts, alerts
4 | Finance & Invoicing | First functional module — priority build
5 | Projects | Project management with milestones & task assignment
6 | Tender / BQ | BQ management, templates & AI auto-fill
7 | HR | Attendance, leave, payroll, clock in/out
8 | Inventory | Stock management & asset borrowing
9 | Profiles | Subcon, client, supplier & org hierarchy
10 | Market Rates | Live Malaysian construction rates
11 | Document Manager | Drag & drop, digital signatures, version control
12 | Mobile PWA | Installable mobile companion app
13 | Settings | Auth, security, billing, API, data export
14 | Safety Module | DOSH + OSHA compliance — incidents, inspections, training
15 | CRM Module | Leads & opportunities tracking — linked to Projects
16 | Fleet Management | Full fleet — location, maintenance, fuel, utilisation & cost

## 📦 Module Requirements
ContractOS — Module Requirements
# | Module | Requirements | Key Features | Responsible Role | Status
1 | Dashboard | • Role-based views per user type • Visual charts, graphs & KPI numbers • Notifications & alerts for important updates | Project mgmt, cost mgmt, item mgmt, invoice generation, site memo | All roles (filtered by role) | ✅ Defined
2 | Projects | • Statuses: Active, On Hold, Completed, Cancelled, Pending Customer, Pending Vendor, Pending Payment • Milestones & deadlines • Task assignment to team members • Document management per project 🆕 ADDED: • RFI (Request For Information) dedicated board per project • Submittals tracking dedicated board per project • Change Orders: value-based approval (small = auto, large = PM & Director) | BQ-linked, profile-linked, docs management, milestone tracking | PM / Admin / Director | ✅ Defined
3 | Tender / BQ | • Pre-built templates + build from scratch • Full version history on every edit • Automation triggers: approval, project creation, manual, scanned upload • AI auto-fill from past BQs & market rates • Admin fine-tune of AI learning | BQ database, automation, AI auto-fill, version control | QS / Estimator / Admin | ✅ Defined
4 | Finance | • Claim management (Full / Progress / Invoice) • Certificate management • Separate from Invoicing module • Optional SST/GST per transaction • Payment statuses: Paid, Unpaid, Overdue, Partially Paid • Weekly escalation for unclosed payment certs (PM & Director) • Finance can advise & check | Claim mgmt, cert mgmt, payment tracking, retention tracking | Finance / Accountant | ✅ Defined
5 | Invoicing | • Separate module from Finance • Create & send invoices • Track payments received • Manage expenses • Multiple currencies • Standard invoice layout • Optional SST/GST toggle per invoice 🆕 ADDED: • Change Orders tracking (linked from Projects) | Invoice creation, payment tracking, expense management | Finance / Admin | ✅ Defined
6 | HR | • Staff attendance tracking • Clock in / Clock out for staff • Leave management with approval flow • Payroll calculation inside system • Overtime tracking & pay • Staff management (Hire, VSS, Removal) • Letter management (Offer, Bonus, KPI, Warning) • User & team management (moved from Settings) | Attendance, leave, payroll, overtime, letters, staff lifecycle | HR / Admin / Director | ✅ Defined
7 | Inventory | • Consumable material tracking • Returnable asset tracking (borrow & return) • Low stock alerts • Auto-generated purchase orders • Direct manager approval for borrowed assets | Stock management, asset borrowing, purchase orders | Admin / Site Supervisor | ✅ Defined
8 | Profiles | • Profile types: Subcon, Client, Supplier, Main Contractor, Organisation • Different access levels per profile type • Profiles active immediately (no approval) • Auto-fill document headers from profile details • Organisation hierarchy reporting | Profile management, hierarchy, document auto-fill | Admin / Clerk | ✅ Defined
9 | Market Rates | • Live Malaysian construction material & labour rates • Sources: Government open data (CIDB, KPKT) + admin override • Historical rate log • Location-based rate adjustment per project site | Live rates, admin override, history log, location rates | Admin / QS | ✅ Defined
10 | Document Manager | • Drag & drop layout editor • All document types supported • Media support (images, files) • Auto-import from profile details • Full version history — all versions kept • No approval workflow needed • Digital signatures inside system | Document creation, editing, version control, digital signatures | All roles | ✅ Defined
11 | Mobile PWA | • Installable APK/iOS on company devices • Modules: Dashboard, HR, Projects, Settings, Profiles, Inventory, Finance • Offline mode — works without internet • Push notifications enabled | Mobile access, offline mode, push notifications | Site Staff / Engineers / Officers | ✅ Defined
12 | Settings | • Authentication & security settings • Subscription & billing management • Logging & audit access (Admin only) • API key management • Data export & backup • Session timeout settings (default 30 min, admin adjustable) | Auth, billing, API, logging, data export, session management | Admin / Director | ✅ Defined
13 | User Management | • Invite, manage & deactivate users • Assign roles & permissions • Moved from Settings — now standalone or under HR • Roles: Director, Admin, PM, QS, Finance, HR, Engineer, Technician, Officer, Internal, Subcon, Client, Supplier | User roles, permissions, invitations, deactivation | Admin / Director | ✅ Defined
14 | Safety | • Site safety programs & SOPs • Incident reporting & investigation • Safety inspections & checklists • Staff safety training records & certifications • DOSH (Malaysia) compliance • OSHA international standard compliance • Safety alerts & non-compliance notifications | Incident reporting, inspections, training records, compliance tracking | Safety Officer / Admin / Director | ✅ New — Added
15 | CRM | • Track new leads & tender opportunities • Client relationship management • Bid opportunity pipeline • Lead status tracking • Link leads to Projects when won • Communication history per lead | Lead tracking, opportunity pipeline, bid management, client history | Director / Admin / PM | ✅ New — Added
16 | Fleet Management | • Vehicle & heavy equipment registry • Real-time location tracking per site • Maintenance schedules & service history • Fuel consumption tracking • Equipment utilisation reports • Cost tracking per vehicle/equipment • Maintenance alerts & reminders | Fleet registry, location, maintenance, fuel, utilisation, cost | Admin / Site Supervisor / Director | ✅ New — Added

## 🔄 Project Lifecycle
ContractOS — Project Lifecycle (Fasa 1–6)
# | Phase | Activity | Key Documents | Responsible | Module | System Automation / Notes
1 | Fasa 1: Tender | Buy Tender Documents | CIDB, SPKK, STB, Payment Receipts | Clerk / PM | Document Manager | Manage all tender documents via own management modules
2 | Fasa 1: Tender | Site Visit | Site Visit Attendance Certificate | PM / Nominee | Projects | Auto-record site visit & import to project site memo
3 | Fasa 1: Tender | Fill BQ & Score Tender | Cost Analysis, Quotations, Profit Margin | QS / Estimator | Tender / BQ | AI auto-fill BQ from past projects & live market rates
4 | Fasa 1: Tender | Prepare Supporting Docs | Bank Statements, Machinery List, Company Profile | Clerk | Document Manager | Help clerk manage & edit docs to match company layout; profile auto-fill
5 | Fasa 1: Tender | Submit Tender | Lacquered Envelope, Submission Receipt | Clerk / Dispatch | Projects | System alerts before tender submission deadlines
6 | Fasa 2: Lantikan | Receive LOA (SST) | SST Original, Letter of Acceptance | Director / PM | Projects / Finance | Save LOA & policy details in Project Management; alert if missing
7 | Fasa 2: Lantikan | Performance Bond & Insurance | CAR, WC, Performance Bond (5%) | Admin / Clerk | Finance | Save bond, insurance & costs in Project Mgmt; alert PM, Admin & Director if expired
8 | Fasa 3: Mula Kerja | Pre-Con Meeting & Mobilisation | Meeting Minutes, Gantt Chart (CPM), TMP | PM / Supervisor | Projects | System auto-generates Gantt draft; user edits; PM alerted on delays
9 | Fasa 4: Kerja Tapak | Execution (Milling/Laying) | Site Diary, Delivery Order (DO) Premix | Site Supervisor | Projects / Document Manager | Handle documentation per BQ scope; unlimited scopes per project
10 | Fasa 4: Kerja Tapak | Lab Test (Coring) | Coring Test Report (Road Thickness) | Lab Tech / PM | Projects | Upload via mobile or desktop; notifies PM & QS upon upload
11 | Fasa 5: Tuntutan | Interim Claim (Progress) | Measurement Sheet, Drawings, Invoice | QS / Clerk | Finance / Document Manager | 1-click generate progress claim; monthly submission per scope
12 | Fasa 5: Tuntutan | Payment Certificate | Payment Cert (Signed by SO) | Client / Treasurer | Finance | Weekly reminder if not closed within 14–30 days; escalate to PM & Director; Finance can advise
13 | Fasa 6: Siap | CPC Certificate | CPC Certificate (Warranty/DLP begins) | PM / Client | Projects / Document Manager | Upload CPC cert to project details upon receipt from client
14 | Fasa 6: Siap | Bank Transfer (EFT) | Payment Voucher, Bank Statement | Accountant | Finance | Validate Malaysian bank format; record SWIFT/BIC; all bank details recorded
15 | Fasa 6: Siap | Retention Release | CMGD Certificate (after 6–12 months DLP) | PM / Clerk | Finance / Projects | Default 10% retention (overridable); alert PM & Finance when release date approaching

## 👥 User Roles & Access
ContractOS — User Roles & Access Matrix
Module / Feature | Director | Admin / PM | QS / Finance | HR | Engineer / Tech | Subcon / Client
Dashboard | ✅ | ✅ | ✅ | ✅ | ✅ | 👁️
Projects (Full) | ✅ | ✅ | 👁️ | ❌ | 👁️ | 👁️
Projects (Own) | ✅ | ✅ | ✅ | ❌ | ✅ | ❌
Tender / BQ | ✅ | ✅ | ✅ | ❌ | 👁️ | ❌
Finance | ✅ | ✅ | ✅ | ❌ | ❌ | ❌
Invoicing | ✅ | ✅ | ✅ | ❌ | ❌ | 👁️
HR — Payroll | ✅ | ✅ | ❌ | ✅ | ❌ | ❌
HR — Attendance | ✅ | ✅ | ❌ | ✅ | ✅ | ❌
HR — Letters | ✅ | ✅ | ❌ | ✅ | ❌ | ❌
Inventory | ✅ | ✅ | ❌ | ❌ | ✅ | ❌
Profiles | ✅ | ✅ | ✅ | ❌ | 👁️ | 👁️
Market Rates | ✅ | ✅ | ✅ | ❌ | 👁️ | ❌
Document Manager | ✅ | ✅ | ✅ | ✅ | ✅ | 👁️
Mobile PWA | ✅ | ✅ | ✅ | ✅ | ✅ | ❌
Settings — Billing | ✅ | ✅ | ❌ | ❌ | ❌ | ❌
Settings — API | ✅ | ✅ | ❌ | ❌ | ❌ | ❌
Audit Logs | ✅ | ❌ | ❌ | ❌ | ❌ | ❌
User Management | ✅ | ✅ | ❌ | ❌ | ❌ | ❌
📖 Legend
✅ | Full Access
👁️ | View Only
❌ | No Access

## 🔐 Security Requirements
ContractOS — Security Requirements (PDPA 2010 ¦ ISO 27001 ¦ SOC 2)
# | Security Area | Framework | Requirement | Implementation Detail | Status
1 | Data Collection & Consent | PDPA 2010 | Consent notice shown at user signup | Collect: name, email, phone, company details, payment info, usage behaviour & uploaded documents | ✅ Defined
2 | Data Storage Location | PDPA 2010 | Primary storage in Malaysia; backup overseas | Overseas backup must meet PDPA-equivalent data protection standards | ✅ Defined
3 | Data Access Control | ISO 27001 | Strict role-based access per user type | 13 user roles defined; each role restricted to relevant modules only | ✅ Defined
4 | Data Breach Protocol | PDPA 2010 / ISO 27001 | Auto-detect suspicious activity & breach | System alerts admin immediately; affected users notified promptly | ✅ Defined
5 | Data Retention & Deletion | PDPA 2010 | Retain data for 7 years after closure/inactivity | Users can request personal data deletion; admin handles deletion | ✅ Defined
6 | Third Party Data Sharing | PDPA 2010 | All third parties listed in Privacy Policy | Covered under general signup consent; no separate consent required | ✅ Defined
7 | Cross-Border Data Transfer | PDPA 2010 | Overseas backup servers must meet PDPA standards | Not mentioned in privacy policy; legal review recommended before launch | ✅ Defined
8 | Audit Logs & Monitoring | ISO 27001 / SOC 2 | Full log of every user action in the system | Logs accessible by Admin only; includes view, edit, delete & export actions | ✅ Defined
9 | Encryption | ISO 27001 / SOC 2 | All data encrypted in transit & at rest | HTTPS/SSL for data in transit; server-side encryption for stored data | ✅ Defined
10 | Authentication Security | ISO 27001 | Optional 2FA + account lockout on failed attempts | 2FA optional per user; account locked after several failed login attempts | ✅ Defined
11 | Session Management | ISO 27001 | Auto logout after inactivity with warning | Default 30-minute timeout; admin can adjust; user warned before expiry | ✅ Defined
12 | API Security | ISO 27001 / SOC 2 | API key authentication + rate limiting | Unique API key required per connection; rate limit per minute to prevent abuse | ✅ Defined
⚠️ Legal Advisory: It is strongly recommended to have a qualified Malaysian legal advisor review ContractOS's Privacy Policy and Terms of Service before public launch to ensure full PDPA 2010 compliance.

## ⚙️ Gap Audit Log
ContractOS — Complete Gap Audit Log
# | Module / Area | Category | Gap / Question | Resolution / Answer | Status
1 | Dashboard | Module Gap | Role-based dashboard views needed? | Yes — different views per user type | ✅ Resolved
2 | Dashboard | Module Gap | Charts & graphs needed? | Yes — visual charts + KPI numbers | ✅ Resolved
3 | Dashboard | Module Gap | Notifications & alerts needed? | Yes — important updates alerted | ✅ Resolved
4 | Projects | Module Gap | Project statuses needed? | Active, On Hold, Completed, Cancelled, Pending Customer, Pending Vendor, Pending Payment | ✅ Resolved
5 | Projects | Module Gap | Milestones & deadlines? | Yes — each project has milestones & deadlines | ✅ Resolved
6 | Projects | Module Gap | Task assignment to team members? | Yes — assign to specific team members | ✅ Resolved
7 | Tender / BQ | Module Gap | BQ templates available? | Both — pre-built templates + build from scratch | ✅ Resolved
8 | Tender / BQ | Module Gap | Version history on BQ edits? | Yes — every change is saved | ✅ Resolved
9 | Tender / BQ | Module Gap | What triggers BQ automation? | On approval, project creation, manual, + scanned BQ upload with AI auto-fill | ✅ Resolved
10 | Finance | Module Gap | Invoicing separate from Finance? | Yes — separate modules | ✅ Resolved
11 | Finance | Module Gap | Tax handling (SST/GST)? | Optional per invoice — some need tax, some don't | ✅ Resolved
12 | Finance | Module Gap | Payment statuses? | Paid, Unpaid, Overdue, Partially Paid | ✅ Resolved
13 | HR | Module Gap | Payroll calculation inside system? | Yes — calculated inside the system | ✅ Resolved
14 | HR | Module Gap | Leave management? | Yes — staff applies & approves inside system | ✅ Resolved
15 | HR | Module Gap | Overtime tracking? | Yes — track hours & pay | ✅ Resolved
16 | HR | Addition | Clock in / Clock out for staff | Added to HR module alongside attendance & payroll | ✅ Resolved
17 | Inventory | Module Gap | Low stock alerts? | Yes — alert when running low | ✅ Resolved
18 | Inventory | Module Gap | Purchase orders for restocking? | Yes — auto-generated by system | ✅ Resolved
19 | Inventory | Module Gap | Who approves borrowed assets? | Direct manager approval | ✅ Resolved
20 | Profiles | Module Gap | Different access per profile type? | Yes — different access levels per profile type | ✅ Resolved
21 | Profiles | Module Gap | Profile approval process? | No — active immediately after creation | ✅ Resolved
22 | Profiles | Module Gap | Auto-fill document headers from profile? | Yes — company name, address etc auto-filled | ✅ Resolved
23 | Market Rates | Module Gap | Data source for live rates? | Both — live government data (CIDB, KPKT) + admin override | ✅ Resolved
24 | Market Rates | Module Gap | Historical rate tracking? | Yes — full log of changes over time | ✅ Resolved
25 | Market Rates | Module Gap | Location-based rate adjustment? | Yes — adjustable per project site | ✅ Resolved
26 | Document Manager | Module Gap | Version history for documents? | Yes — all versions kept | ✅ Resolved
27 | Document Manager | Module Gap | Approval workflow for documents? | No — not needed | ✅ Resolved
28 | Document Manager | Module Gap | Digital signatures? | Yes — inside the system | ✅ Resolved
29 | Mobile PWA | Module Gap | Which modules on mobile? | Dashboard, HR, Projects, Settings, Profiles, Inventory, Finance | ✅ Resolved
30 | Mobile PWA | Module Gap | Offline mode? | Yes — works without internet on site | ✅ Resolved
31 | Mobile PWA | Module Gap | Push notifications? | Yes — enabled | ✅ Resolved
32 | Settings | Module Gap | Subscription & billing inside system? | Yes — managed inside the system | ✅ Resolved
33 | Settings | Module Gap | User & team management location? | Moved to HR or dedicated User module | ✅ Resolved
34 | Settings | Module Gap | Data export & backup? | Yes — users can export & backup | ✅ Resolved
35 | Fasa 1 — BQ | Workflow Gap | How does system learn from past BQs? | Auto-learn from past BQs + admin can fine tune | ✅ Resolved
36 | Fasa 2 — LOA | Workflow Gap | Alerts for missing/expired LOA or bond? | Yes — auto alert PM, Admin & Director | ✅ Resolved
37 | Fasa 3 — Gantt | Workflow Gap | Who creates the Gantt chart? | System auto-generates draft; user can edit; PM alerted on delays | ✅ Resolved
38 | Fasa 4 — BQ | Workflow Gap | BQ scope limit per project? | No limit — unlimited scopes; each tracked independently | ✅ Resolved
39 | Fasa 4 — Coring | Workflow Gap | Who uploads coring test report? | Both mobile (site) or desktop (office); notifies PM & QS | ✅ Resolved
40 | Fasa 5 — Claims | Workflow Gap | Difference: full claim vs progress claim? | Progress = monthly per scope; Full = 100% final; separate templates | ✅ Resolved
41 | Fasa 5 — Payment | Workflow Gap | Escalation if payment cert not closed after 30 days? | Weekly alerts to PM, Director & Finance until resolved | ✅ Resolved
42 | Fasa 6 — Retention | Workflow Gap | Retention amount fixed or variable? | Default 10% overridable per project; alert PM & Finance when approaching | ✅ Resolved
43 | Security | Security Gap | Data collection & consent (PDPA)? | Consent notice at signup; collect all data types | ✅ Resolved
44 | Security | Security Gap | Data storage location (PDPA)? | Primary Malaysia; backup overseas (PDPA-equivalent standards) | ✅ Resolved
45 | Security | Security Gap | Role-based access control (ISO 27001)? | Strict access per role; 13 user roles defined | ✅ Resolved
46 | Security | Security Gap | Data breach protocol (PDPA / ISO 27001)? | Auto-detect; alert admin; notify affected users | ✅ Resolved
47 | Security | Security Gap | Data retention & deletion (PDPA)? | 7 years retention; users can request deletion | ✅ Resolved
48 | Security | Security Gap | Third party data sharing (PDPA)? | Listed in privacy policy; covered under signup consent | ✅ Resolved
49 | Security | Security Gap | Cross-border data transfer (PDPA)? | Overseas backup must meet PDPA-equivalent standards | ✅ Resolved
50 | Security | Security Gap | Audit logs & monitoring (ISO 27001 / SOC 2)? | Full logs every action; Admin only access | ✅ Resolved
51 | Security | Security Gap | Encryption (ISO 27001 / SOC 2)? | HTTPS/SSL in transit; encrypted at rest on servers | ✅ Resolved
52 | Security | Security Gap | Authentication security (ISO 27001)? | Optional 2FA; account lockout on failed attempts | ✅ Resolved
53 | Security | Security Gap | Session management (ISO 27001)? | Default 30 min; admin adjustable; warn before expiry | ✅ Resolved
54 | Security | Security Gap | API security (ISO 27001 / SOC 2)? | Unique API key per connection; rate limiting per minute | ✅ Resolved
📊 Audit Summary — Total Gaps Resolved: 54

## 💰 Pricing & Subscriptions
ContractOS — Pricing & Subscription Model
💼 Business Model Overview
Property | Detail
Model | Freemium — Free basic tier + Paid advanced features
Trial Period | 5-day free trial on all paid/advanced features
Billing Cycles | Monthly & Yearly (yearly subscription gets discount)
Pricing Structure | Tiered plans — Per user OR per company
Auto-Renewal | On by default — users can disable
Payment Methods | FPX (Malaysian online banking) & Credit/Debit Card
Payment Gateway | Stripe (PCI DSS Level 1 — enterprise grade)
📦 Subscription Tiers
Feature / Module | Free (Basic) | Pro | Business | Enterprise
Dashboard | ✅ Basic | ✅ Full | ✅ Full | ✅ Full + Custom
Projects | ✅ Up to 3 | ✅ Unlimited | ✅ Unlimited | ✅ Unlimited
Finance & Invoicing | ✅ Limited | ✅ Full | ✅ Full | ✅ Full
Tender / BQ | ❌ | ✅ Full | ✅ Full + AI | ✅ Full + AI
HR Module | ✅ Basic | ✅ Full | ✅ Full | ✅ Full
Inventory | ❌ | ✅ Full | ✅ Full | ✅ Full
Market Rates (Live) | ❌ | ✅ | ✅ | ✅
Document Manager | ✅ Basic | ✅ Full | ✅ Full | ✅ Full
Mobile PWA | ✅ View only | ✅ Full | ✅ Full | ✅ Full
Reports & Export | PDF only | PDF & Excel | All formats | All formats + Scheduled
Multi-Subsidiary | ❌ | ❌ | ❌ | ✅ Enterprise only
Custom Email Domain | ❌ | ❌ | ❌ | ✅ Enterprise only
Email Customisation | ❌ | ✅ Basic | ✅ Full | ✅ Full branded
API Access | ❌ | ❌ | ✅ | ✅ Full
Support | Help Centre | Help Centre + Email | Email + Live Chat | Dedicated Support
Users Allowed | Up to 3 | Up to 15 | Up to 50 | Unlimited

## 🚀 Onboarding Flow
ContractOS — User Onboarding Flow
Step | Stage | Description | System Action | Status
1 | Landing Page | Visitor arrives at ContractOS landing page | Show hero, features, pricing & Get Started CTA | ✅
2 | Signup | User clicks Get Started & fills signup form | Collect name, email, company name, password | ✅
3 | Email Verification | System sends verification email to user | User must verify email before accessing system | ✅
4 | Plan Selection | User selects subscription plan or starts free tier | Show tier comparison; start 5-day trial for paid features | ✅
5 | Payment (if paid) | User enters payment details via Stripe | Process FPX or card payment; confirm subscription | ✅
6 | Setup Wizard | Step-by-step company profile setup begins | Collect: company name, logo, address, SSM no., contacts | ✅
7 | Branding Setup | User uploads company logo & sets brand colours | Apply branding to documents, emails & workspace | ✅
8 | Team Invitation | Admin invites team members to join workspace | System sends invite emails to team members | ✅
9 | Role Assignment | Admin assigns roles to each team member | Set permissions per user based on role | ✅
10 | Guided Tour | First-time dashboard loads with guided tour | Show tooltips & walkthrough of key features | ✅
11 | First Project | System prompts user to create first project | Quick-start template available to begin immediately | ✅
12 | Active | User is fully onboarded & using ContractOS | AI chatbot available for instant help anytime | ✅

## 🔔 Notifications
ContractOS — Notification System
📡 Notification Channels & Settings
Channel | Available | Critical Alerts | Daily Digest | User Can Customise
In-App Notifications | ✅ | ✅ Instant | ✅ | Partial
Email | ✅ | ✅ Instant | ✅ | Partial
WhatsApp Business API | ✅ | ✅ Instant | ✅ | Partial
SMS | ❌ Not included | — | — | —
🔔 Notification Types — Fixed vs Customisable
Notification Type | Trigger | Channel | Timing | Fixed / Customisable
Data Breach Alert | Security incident detected | In-app + Email | Instant | 🔒 Fixed
Account Lockout | Multiple failed login attempts | In-app + Email | Instant | 🔒 Fixed
Session Expiry Warning | 30 min inactivity approaching | In-app | Instant | 🔒 Fixed
Payment Cert Overdue | Not closed after 30 days | In-app + Email + WhatsApp | Weekly | 🔒 Fixed
LOA / Bond Expiry | Document expiring soon | In-app + Email + WhatsApp | Instant | 🔒 Fixed
Gantt Chart Delay | Task behind schedule | In-app + Email | Instant | 🔒 Fixed
Invoice Due | Payment approaching due date | In-app + Email | Instant | ⚙️ Customisable
Low Stock Alert | Inventory below threshold | In-app + Email | Instant | ⚙️ Customisable
Task Assignment | New task assigned to user | In-app + WhatsApp | Instant | ⚙️ Customisable
Report Ready | Scheduled report generated | Email | Scheduled | ⚙️ Customisable
Coring Test Uploaded | New test report added | In-app + Email | Instant | ⚙️ Customisable
Retention Release Due | DLP period ending | In-app + Email + WhatsApp | Instant | ⚙️ Customisable
Leave Request | Staff submits leave application | In-app | Instant | ⚙️ Customisable
New Team Member | User invited to workspace | Email | Instant | ⚙️ Customisable

## 📊 Reports & Analytics
ContractOS — Reports & Analytics
Report Type | Description | Export Formats | Generation | Who Can Access
Project Progress Report | Status, milestones, delays & completion % per project | PDF, Excel, Word, CSV | Manual + Scheduled | Director, Admin, PM
Financial Summary Report | Income, expenses, claims, outstanding payments | PDF, Excel, Word, CSV | Manual + Scheduled | Director, Finance, Admin
Invoice Report | All invoices — paid, unpaid, overdue, partially paid | PDF, Excel, CSV | Manual + Scheduled | Finance, Admin
Claim Report | Progress & full claims per project | PDF, Word, Excel | Manual | Finance, QS, Admin
HR Attendance Report | Clock in/out, leave taken, overtime per staff | PDF, Excel, CSV | Manual + Scheduled | HR, Admin, Director
Payroll Report | Salary, overtime & deductions per period | PDF, Excel | Manual + Scheduled | HR, Finance, Director
Inventory Stock Report | Current stock levels, low stock items, borrowed assets | PDF, Excel, CSV | Manual + Scheduled | Admin, Site Supervisor
BQ Cost Report | Estimated vs actual cost per BQ scope | PDF, Excel | Manual | QS, PM, Director
Market Rates Report | Current & historical rates by material & location | PDF, Excel, CSV | Manual | QS, Admin
Audit Log Report | Full system action log by user | PDF, CSV | Manual | Admin only
Retention Report | Retention amounts held & release dates per project | PDF, Excel | Manual + Scheduled | Finance, PM, Director
Document Activity Report | Documents created, edited, signed & versions | PDF, CSV | Manual | Admin, PM

## 🏢 Multi-Tenancy
ContractOS — Multi-Tenancy Architecture
Feature | Description | Available On | Status
Workspace Separation | Each company has its own fully private & isolated workspace. No data is shared between companies. | All tiers | ✅ Defined
Standard Account (Free/Pro/Business) | One company per account only. All data scoped to that single company. | Free / Pro / Business | ✅ Defined
Enterprise Account | Multi-subsidiary support unlocked. Parent company can manage multiple subsidiaries under one account. | Enterprise only | ✅ Defined
Company Branding | Each company can upload their own logo and set brand colours applied across their workspace. | All tiers | ✅ Defined
Data Isolation | No cross-tenant data access. Each company's data is stored and accessed independently. | All tiers | ✅ Defined
User Scope | Users belong to one company workspace only. Cannot access another company's workspace. | All tiers | ✅ Defined
Custom Email Domain | Available on Enterprise tier only. Companies can send emails from their own domain. | Enterprise only | ✅ Defined
Billing Isolation | Each company manages and pays for their own subscription independently. | All tiers | ✅ Defined

## 💳 Payment Gateway
ContractOS — Payment Gateway (Stripe)
Feature | Setting / Value | Notes | Status
Payment Gateway | Stripe | Enterprise-grade, PCI DSS Level 1 compliant | ✅ Defined
Payment Methods | FPX + Credit/Debit Card | Malaysian online banking + Visa/Mastercard | ✅ Defined
Billing — Monthly | Charged every month | Auto-renews monthly until cancelled | ✅ Defined
Billing — Yearly | Charged once per year | Discounted rate vs monthly; auto-renews yearly | ✅ Defined
Auto-Renewal | On by default | Users can disable auto-renewal in account settings | ✅ Defined
Free Tier | No payment required | Access to basic features without any charge | ✅ Defined
5-Day Trial | Paid features unlocked for 5 days | No charge during trial; card required to start | ✅ Defined
Failed Payment | System retries & alerts user | Account downgraded if payment fails after grace period | ✅ Defined
Refund Policy | To be defined by legal team | Recommended: pro-rated refunds for yearly plans | ✅ Defined
Invoice/Receipt | Auto-generated after each payment | Sent to user's registered email via Stripe | ✅ Defined
Currency | MYR (Malaysian Ringgit) primary | Multi-currency support via Stripe | ✅ Defined
Compliance | PCI DSS Level 1 | Stripe handles all card data — ContractOS never stores card details | ✅ Defined

## 🎨 Branding & Design
ContractOS — Branding & Design Identity
🎨 Brand Colours
Colour Name | Hex Code | Usage | Preview
Navy | #0D1B2E / #1B2A4A | Primary — backgrounds, headers, sidebar | Navy
Gold | #C9A84C | Accent — highlights, CTA buttons, icons | Gold
Green | #065F46 / #12B76A | Success states, active indicators, status | Green
Grey | #667085 / #F2F4F7 | Secondary text, borders, backgrounds | Grey
Maroon | #7B1C1C | Alerts, warnings, urgent indicators | Maroon
White | #FFFFFF | Content areas, cards, text on dark backgrounds | White
🔤 Typography & UI
Element | Value | Notes
Primary Font | Inter | All text across the platform
Logo Style | Text-based (for now) | ContractOS wordmark — no icon yet
Heading Size | 32px / 24px / 18px | H1 / H2 / H3 hierarchy
Body Text Size | 14px / 16px | Default content text
Button Style | Rounded corners, bold text | Primary: Gold bg, Secondary: Navy outline
Dark Theme | Yes — primary UI theme | Navy backgrounds with light text
Light Mode | Optional — future consideration | Not in initial build
Icon Style | Line icons — clean & modern | Consistent with Inter font aesthetic

## 🌐 Landing Page
ContractOS — Landing Page Specification
# | Section | Content Description | Language | Status
1 | Navigation Bar | Logo (text-based), links to Features/Pricing/FAQ/Contact, Language toggle (EN/BM), Login & Get Started buttons | EN + BM | ✅
2 | Hero Section | Main headline, subheadline describing ContractOS, Get Started CTA button, platform screenshot/mockup | EN + BM | ✅
3 | Features Section | Highlight key modules: Projects, Finance, BQ, HR, Inventory, Document Manager — icons + short descriptions | EN + BM | ✅
4 | Pricing Section | Show all 4 tiers (Free, Pro, Business, Enterprise) with feature comparison table and Get Started / Contact Sales CTA | EN + BM | ✅
5 | Testimonials Section | Customer reviews / case studies — placeholder until real clients available | EN + BM | ✅
6 | FAQ Section | Common questions about ContractOS — billing, features, security, mobile app | EN + BM | ✅
7 | Contact Section | Contact form — name, email, company, message; WhatsApp button; email address | EN + BM | ✅
8 | Footer | Logo, links, social media, privacy policy, terms of service, copyright | EN + BM | ✅

## 📧 Email System
ContractOS — Email System Specification
Email Type | Description | Sender | Customisable | Tier Required
Welcome Email | Sent when user successfully signs up | ContractOS default | Logo + colours | All tiers
Email Verification | Sent to verify email before first login | ContractOS default | Fixed | All tiers
Password Reset | Sent when user requests password reset | ContractOS default | Fixed | All tiers
Invoice Email | Sent when invoice is issued to a client | Company or ContractOS | ✅ Full customise | Pro & above
Claim Notification | Sent when a claim is submitted or updated | Company or ContractOS | ✅ Full customise | Pro & above
Payment Reminder | Sent when invoice/cert is overdue | Company or ContractOS | ✅ Full customise | Pro & above
Scheduled Report | Auto-sent on defined schedule | ContractOS default | Logo + colours | Business & above
Alert Notification | System alerts (breach, overdue, expiry) | ContractOS default | Fixed | All tiers
Team Invitation | Sent when admin invites a team member | ContractOS default | Logo only | All tiers
Subscription Receipt | Auto-sent after each payment via Stripe | Stripe + ContractOS | Fixed | Paid tiers
Custom Domain Email | Emails sent from company's own domain | Company domain | ✅ Full customise | Enterprise only

## 🔗 Integrations
ContractOS — Third Party Integrations
Integration | Category | Purpose | Tier Required | Status
Stripe | Payment Gateway | Subscription billing, FPX & card payments, receipts | All tiers | ✅ Defined
SQL Account | Accounting | Sync financial data with Malaysian accounting software | Business & above | ✅ Defined
QuickBooks | Accounting | Export/sync invoices & financial records | Business & above | ✅ Defined
Xero | Accounting | Cloud accounting integration for finance module | Business & above | ✅ Defined
DocuSign | E-Signature | Digital signing of contracts & documents | Pro & above | ✅ Defined
MyEG | E-Signature / Gov | Malaysian government e-signature platform | Pro & above | ✅ Defined
WhatsApp Business API | Notifications | Send alerts, reminders & notifications via WhatsApp | All tiers | ✅ Defined
Google Calendar | Calendar | Sync project milestones, deadlines & meetings | Pro & above | ✅ Defined
Outlook Calendar | Calendar | Sync project milestones, deadlines & meetings | Pro & above | ✅ Defined
CIDB Portal | Government Data | Live market rates for construction materials & labour | All tiers | ✅ Defined
KPKT Portal | Government Data | Housing & construction regulatory data | All tiers | ✅ Defined
AWS S3 | Cloud Storage | Document & file storage for all uploaded content | All tiers (backend) | ✅ Defined

## 🆘 Support System
ContractOS — Support & Help System
Support Channel | Description | Available To | Status
Help Centre | Articles, guides & how-to documentation for all modules | All tiers | ✅ Defined
Email Support | Users submit support tickets via email; response within defined SLA | All tiers | ✅ Defined
Live Chat by Appointment | Scheduled live chat sessions with support team — not always-on | All tiers | ✅ Defined
AI Chatbot | Instant answers to common questions inside the platform 24/7 | All tiers | ✅ Defined
Guided Tour | Interactive walkthrough shown on first login for new users | All tiers | ✅ Defined
Tooltips | Contextual hints shown on hover throughout the platform | All tiers | ✅ Defined
Video Tutorials | Future consideration — short how-to videos per module | TBD | 📋 Future
Community Forum | Future consideration — user community Q&A platform | TBD | 📋 Future

## ☁️ Hosting & Domain
ContractOS — Hosting & Infrastructure
Infrastructure Item | Value / Selection | Notes | Status
Cloud Provider | AWS (Amazon Web Services) | Enterprise-grade, globally trusted, Malaysia region available | ✅ Defined
Primary Server Region | AWS Asia Pacific — Kuala Lumpur (ap-southeast-3) | Satisfies PDPA 2010 data residency in Malaysia | ✅ Defined
Backup Server Region | AWS Global (e.g. Singapore / Ireland) | Geo-redundant backup; must meet PDPA-equivalent standards | ✅ Defined
Domain Name | Not decided yet | To be confirmed — recommend contractos.com or contractos.my | 📋 Pending
SSL Certificate | Yes — HTTPS enforced across all pages | Managed via AWS Certificate Manager | ✅ Defined
CDN | AWS CloudFront | Fast content delivery globally for web & mobile PWA | ✅ Defined
File Storage | AWS S3 | All documents, images & uploaded files stored securely | ✅ Defined
Database | AWS RDS (Relational Database) | Managed, scalable database with automatic backups | ✅ Defined
Uptime Target | 99.9% SLA | Standard AWS infrastructure uptime guarantee | ✅ Defined
Disaster Recovery | Automated daily backups | Point-in-time recovery available via AWS RDS | ✅ Defined
Scalability | Auto-scaling enabled | System scales up automatically during high traffic | ✅ Defined
Monitoring | AWS CloudWatch | Real-time performance, error & security monitoring | ✅ Defined

## 🏆 Competitor Analysis
ContractOS vs ConstructOS — Feature Comparison
🔍 Side-by-Side Feature Comparison
Feature / Module | ConstructOS | ContractOS | ContractOS Advantage | Status
Dashboard | ✅ Basic | ✅ Role-based + Charts + Alerts | Role-specific views & smart notifications | ✅ Stronger
HR Management | ✅ Workforce + Certs | ✅ Full HR + Payroll + Clock In/Out | Payroll, overtime, leave, letters & clock in/out | ✅ Stronger
Project Management | ✅ 10 Boards | ✅ Full + RFI + Submittals + Change Orders | BQ-linked, milestone alerts, unlimited scopes | ✅ Stronger
CRM | ✅ Full CRM | ✅ Leads & opportunities | Lighter but sufficient; linked to Projects | ⚡ Comparable
Estimating / BQ | ✅ Basic estimating | ✅ Full BQ + AI auto-fill + Market rates | AI learning from past BQs + live CIDB/KPKT data | ✅ Stronger
Finance & Claims | ✅ Basic cost tracking | ✅ Full claims, certs, retention, tax | Progress/full claims, payment certs, SST/GST | ✅ Stronger
Invoicing | ✅ Basic | ✅ Full multi-currency invoicing | Multi-currency, SST/GST toggle, payment tracking | ✅ Stronger
Safety Module | ✅ OSHA compliance | ✅ DOSH + OSHA compliance | Malaysian DOSH + international OSHA standards | ✅ Stronger
Fleet Management | ✅ Full fleet | ✅ Full fleet + fuel + cost | Location, maintenance, fuel, utilisation & cost | ✅ Comparable
Inventory | ❌ Not available | ✅ Stock + assets + purchase orders | Consumables, returnable assets, auto PO | ✅ Stronger
Document Manager | ✅ Basic | ✅ Drag & drop + digital sig + versions | Full version history, digital signatures, auto-fill | ✅ Stronger
Market Rates | ❌ Not available | ✅ Live CIDB/KPKT + location rates | Malaysian-specific live construction rates | ✅ Unique
Mobile PWA | ❌ Not available | ✅ Offline capable installable app | Works offline on site — unique advantage | ✅ Unique
Tender Management | ❌ Not available | ✅ Full tender + BQ database | End-to-end tender lifecycle management | ✅ Unique
Payment Certificates | ❌ Not available | ✅ Full cert tracking + reminders | Smart follow-up reminders to PM & Director | ✅ Unique
Retention Management | ❌ Not available | ✅ 10% default + DLP alerts | Retention tracking with release date reminders | ✅ Unique
WhatsApp Notifications | ❌ Not available | ✅ WhatsApp Business API | Instant WhatsApp alerts for Malaysian users | ✅ Unique
Malaysian Tax (SST/GST) | ❌ Not available | ✅ Optional per invoice | Built-in Malaysian tax compliance | ✅ Unique
PDPA 2010 Compliance | ❌ Not available | ✅ Full PDPA compliance | Malaysian data protection law built-in | ✅ Unique
Multi-Currency | ❌ Not available | ✅ Full multi-currency | Essential for international contractors | ✅ Stronger
Freemium Model | ❌ Demo only | ✅ Free tier + paid plans | Lower barrier to entry for new users | ✅ Stronger
Accounting Integration | ✅ QuickBooks, Sage | ✅ SQL, QuickBooks, Xero | SQL Account — Malaysia's most used accounting sw | ✅ Stronger
E-Signature | ✅ DocuSign | ✅ DocuSign + MyEG | MyEG — Malaysian government e-signature | ✅ Stronger
Calendar Integration | ❌ Not listed | ✅ Google + Outlook | Sync milestones & deadlines to calendar | ✅ Stronger
Government Portal Integration | ❌ Not available | ✅ CIDB + KPKT | Live government data feeds | ✅ Unique
AI / Automation | ✅ Make.com + ChatGPT | ✅ Built-in AI for BQ + Document | Native AI without third-party dependency | ✅ Comparable
RFI Tracking | ✅ Dedicated board | ✅ Dedicated board per project | Formal RFI log & status tracking | ⚡ Comparable
Submittals Tracking | ✅ Dedicated board | ✅ Dedicated board per project | Shop drawings, samples & method statements | ⚡ Comparable
Change Orders | ✅ With audit trail | ✅ Value-based approval workflow | Smart approval: small = auto, large = escalate | ✅ Stronger
Built on | monday.com + Make.com | Custom built — fully owned | Full ownership, no third-party platform dependency | ✅ Stronger
📊 Competitive Summary
✅ ContractOS Stronger | 16 features
✅ ContractOS Unique (not in ConstructOS) | 9 features
⚡ Comparable | 5 features

## 🛡️ Safety Module
ContractOS — Safety Module (DOSH + OSHA)
Feature | Description | Compliance | Responsible Role | Status
Safety Programs & SOPs | Create, manage & distribute site safety programs and standard operating procedures | DOSH + OSHA | Safety Officer / Admin | ✅ Defined
Incident Reporting | Log, investigate & track workplace accidents, near-misses & dangerous occurrences | DOSH Act 1994 + OSHA | Site Supervisor / Safety Officer | ✅ Defined
Safety Inspections | Schedule & conduct regular site safety inspections with digital checklists | DOSH + OSHA | Safety Officer / PM | ✅ Defined
Safety Checklists | Pre-built & customisable safety checklists for different work types & site conditions | DOSH + OSHA | Site Supervisor / Safety Officer | ✅ Defined
Staff Training Records | Track safety training completed, certifications held & renewal dates per staff member | DOSH + OSHA | HR / Safety Officer | ✅ Defined
Certification Tracking | Monitor expiry of safety certifications (e.g. CIDB Green Card, First Aid) with renewal alerts | DOSH Malaysia | HR / Admin | ✅ Defined
Safety Alerts | Automatic alerts for expired certs, overdue inspections & unresolved incidents | DOSH + OSHA | Safety Officer / Director | ✅ Defined
Non-Compliance Notifications | Alert PM & Director when safety standards are not met on site | DOSH + OSHA | Safety Officer / Director | ✅ Defined
HIRARC Documentation | Hazard Identification, Risk Assessment & Risk Control records per project | DOSH Malaysia | Safety Officer / PM | ✅ Defined
Method Statements | Create & store safe work method statements linked to project BQ scopes | DOSH + OSHA | PM / Safety Officer | ✅ Defined
Safety Dashboard | Overview of site safety status, open incidents, pending inspections & cert renewals | DOSH + OSHA | Director / Safety Officer | ✅ Defined
Mobile Safety Reporting | Site staff can submit incident reports & inspection results via mobile PWA | DOSH + OSHA | Site Staff / Supervisor | ✅ Defined

## 🎯 CRM Module
ContractOS — CRM Module (Leads & Opportunities)
Feature | Description | Lead Status | Responsible Role | Status
Lead Registry | Create & manage new leads — company name, contact person, project type, estimated value | New Lead | Director / Admin / PM | ✅ Defined
Opportunity Pipeline | Visual pipeline showing leads by stage: New → Qualified → Tender Submitted → Won / Lost | All stages | Director / PM | ✅ Defined
Bid Opportunity Tracking | Track tender opportunities, submission deadlines & bid status per lead | Tender Stage | PM / QS | ✅ Defined
Lead Status Management | Statuses: New, Contacted, Qualified, Tender Submitted, Won, Lost, On Hold | All stages | Director / PM | ✅ Defined
Communication History | Log all communications (calls, emails, meetings) linked to each lead | All stages | Director / PM / Admin | ✅ Defined
Convert Lead to Project | One-click convert a Won lead into a full Project in the Projects module | Won | PM / Director | ✅ Defined
Follow-up Reminders | Automatic reminders to follow up on leads that have been inactive for a set period | All stages | PM / Director | ✅ Defined
CRM Dashboard | Summary of total leads, pipeline value, win rate & recent activity | All stages | Director / Admin | ✅ Defined
Lead Source Tracking | Track where leads came from: referral, tender portal, direct, social media, etc. | New Lead | Admin / Director | ✅ Defined
CRM Reports | Export leads, pipeline & win/loss reports in PDF, Excel & CSV | All stages | Director / Admin | ✅ Defined

## 🚛 Fleet Management
ContractOS — Fleet Management Module
Feature | Description | Category | Responsible Role | Status
Vehicle & Equipment Registry | Register all company vehicles, machinery & heavy equipment with full details (plate no., model, year, capacity) | Registry | Admin / Director | ✅ Defined
Site Allocation Tracking | Track which vehicle/equipment is assigned to which project site at any time | Location | Admin / Site Supervisor | ✅ Defined
Maintenance Scheduling | Schedule regular servicing, inspections & repairs for each vehicle/equipment | Maintenance | Admin / Fleet Manager | ✅ Defined
Service History Log | Full history of all maintenance, repairs & inspections per vehicle/equipment | Maintenance | Admin / Fleet Manager | ✅ Defined
Maintenance Alerts | Automatic reminders for upcoming scheduled maintenance or overdue services | Maintenance | Admin / Director | ✅ Defined
Fuel Consumption Tracking | Log fuel fill-ups, consumption rates & cost per vehicle/equipment | Fuel | Admin / Site Supervisor | ✅ Defined
Utilisation Reports | Track usage hours, idle time & productivity per vehicle/equipment per project | Utilisation | Admin / Director | ✅ Defined
Cost Tracking | Track total operating cost per vehicle: fuel + maintenance + insurance + depreciation | Cost | Finance / Admin | ✅ Defined
Insurance & Roadtax Tracking | Monitor expiry dates for vehicle insurance, roadtax & permits — auto alert before expiry | Compliance | Admin / Director | ✅ Defined
Fleet Dashboard | Overview of all vehicles — status, location, upcoming maintenance & cost summary | Dashboard | Director / Admin | ✅ Defined
Mobile Fleet Updates | Site staff can log fuel, report issues & update equipment location via mobile PWA | Mobile | Site Staff / Supervisor | ✅ Defined
Fleet Reports | Export fleet cost, utilisation & maintenance reports in PDF, Excel & CSV | Reports | Director / Finance | ✅ Defined

## 📋 RFI, Submittals & CO
ContractOS — RFI, Submittals & Change Orders
📝 RFI — Request For Information
Feature | Description | Directed To | Responsible Role | Status
RFI Log per Project | Dedicated RFI board inside each project — all RFIs in one place | Client / Consultant | PM / QS | ✅ Defined
RFI Creation | Raise formal RFI with subject, description, reference drawings & urgency level | Client / Consultant | PM / QS / Engineer | ✅ Defined
RFI Status Tracking | Statuses: Draft, Submitted, Under Review, Responded, Closed | Client / Consultant | PM | ✅ Defined
RFI Response Recording | Record & attach client/consultant response to each RFI | Client / Consultant | PM / Admin | ✅ Defined
RFI Deadline Alerts | Auto-alert PM if RFI response is not received within expected timeframe | Client / Consultant | PM / Director | ✅ Defined
RFI Reports | Export full RFI log per project in PDF or Excel | Client / Consultant | PM / QS | ✅ Defined
📐 Submittals — Shop Drawings, Samples & Method Statements
Feature | Description | Submittal Type | Responsible Role | Status
Submittals Log | Dedicated submittals board inside each project | All types | PM / QS / Engineer | ✅ Defined
Submittal Creation | Submit shop drawings, material samples, method statements & technical data sheets | Drawings / Samples / Methods | Engineer / QS | ✅ Defined
Review & Approval Tracking | Track submittal status: Submitted, Under Review, Approved, Rejected, Resubmit | All types | PM / Consultant | ✅ Defined
Revision Management | Track resubmissions & revisions per submittal with version history | All types | Engineer / PM | ✅ Defined
Approval Deadline Alerts | Auto-alert PM if submittal review is overdue | All types | PM / Director | ✅ Defined
Submittals Reports | Export full submittals log per project in PDF or Excel | All types | PM / QS | ✅ Defined
🔄 Change Orders — Scope & Cost Changes
Feature | Description | Approval Rule | Responsible Role | Status
Change Order Log | Dedicated change order tracking inside Projects & Finance modules | N/A | PM / Finance | ✅ Defined
Change Order Creation | Log scope, cost & timeline changes with description, reason & impact assessment | N/A | PM / QS | ✅ Defined
Value-Based Approval | Small changes: auto-approved. Large changes: require PM & Director approval | Value threshold | PM / Director | ✅ Defined
Approval Workflow | Multi-level approval for large change orders with audit trail | Large CO only | PM / Director | ✅ Defined
Budget Impact Tracking | Automatically update project budget & BQ when change order is approved | Post-approval | Finance / QS | ✅ Defined
Change Order Status | Statuses: Draft, Pending Approval, Approved, Rejected, Implemented | All stages | PM / Finance | ✅ Defined
Linked to Finance | Approved change orders automatically reflect in Finance & Invoicing modules | Post-approval | Finance | ✅ Defined
Change Order Reports | Export all change orders per project in PDF, Excel & CSV | N/A | PM / Finance / Director | ✅ Defined

## 📅 3-Month MVP Plan
ContractOS — 3-Month MVP Build Plan (In-House Dev Team)
Duration: 3 Months ¦ Sprints: 6 × 2 Weeks ¦ Team: 8 People ¦ Goal: All Modules Basic & Working
Sprint | Period | Goal | Modules / Tasks | Key Deliverable | Status
Sprint 1 | Weeks 1–2 | Foundation & Infrastructure | • AWS setup (RDS, S3, CloudFront, SES) • Design system (colours, fonts, components) • Landing page (Hero, Features, Pricing, FAQ, Contact, Footer) • Login & signup with email verification • Password reset flow • Setup wizard — company profile onboarding • User roles & permissions (13 roles defined) | Infrastructure live + Landing page published | 🔲 Planned
Sprint 2 | Weeks 3–4 | Dashboard & Profiles | • Role-based dashboard (different view per user type) • KPI summary cards & basic charts • In-app notifications & basic email alerts • Profiles module (Subcon, Client, Supplier, Main Contractor) • User management (invite, assign roles, deactivate) • Settings — session timeout, basic API config | First usable screen after login — dashboard live | 🔲 Planned
Sprint 3 | Weeks 5–6 | Finance & Invoicing | • Invoice creation — standard layout, multi-currency • SST/GST toggle per invoice • Invoice tracking — Paid, Unpaid, Overdue, Partially Paid • Basic claim management (Progress & Full) • Payment certificate tracking • Stripe integration — FPX + credit/debit card • Subscription billing — Free, Pro, Business, Enterprise tiers • Basic expense management | Priority module fully working — payments live | 🔲 Planned
Sprint 4 | Weeks 7–8 | Projects & HR | • Project creation — status, team assignment, dates • Milestone & deadline tracking • Basic Gantt chart view (manual build, no AI yet) • Task assignment to team members • HR — clock in / clock out with timestamp • HR — leave application & approval workflow • HR — basic payroll calculation (salary + OT) • HR — attendance log & summary | Core operational modules working for site teams | 🔲 Planned
Sprint 5 | Weeks 9–10 | BQ, Inventory, Document Manager & Settings | • Tender/BQ — create BQ, add line items, basic version history • Market rates — manual entry (live CIDB API in Phase 2) • Inventory — add items, track stock levels, low stock alert • Asset borrowing — manager approval workflow • Document Manager — upload, organise, basic drag & drop • Auto-fill document headers from profile details • Settings — data export, backup, audit log (admin only) | Construction-specific modules working | 🔲 Planned
Sprint 6 | Weeks 11–12 | Remaining Modules + QA & Launch | • CRM — add leads, pipeline view, status tracking • Safety — incident log, inspection checklist (DOSH/OSHA) • Fleet — register vehicles, assign to project site • Mobile PWA — installable on phone (Dashboard, HR, Projects, Finance) • RFI — basic log per project • Submittals — basic log per project • Change orders — create, value-based approval • Full QA testing across all modules • Bug fixes, performance checks, security review • MVP launch to pilot users | All modules live — MVP ready for pilot users | 🔲 Planned

## 👥 Team Structure
ContractOS — In-House Development Team Structure
👥 Core MVP Team (8 People)
Role | Responsibility | Count | Sprint Focus | Must-Have Skills | Type
Tech Lead / Architect | System architecture, AWS setup, code review, technical decisions | 1 | All sprints | AWS, Node.js, PostgreSQL, React, Security | In-house
Frontend Developer (Senior) | UI screens, dashboard, all module interfaces, PWA | 1 | Sprint 2–6 | React.js, Tailwind CSS, PWA, REST APIs | In-house
Frontend Developer (Mid) | Supporting UI build, forms, tables, components | 1 | Sprint 2–6 | React.js, HTML/CSS, responsive design | In-house
Backend Developer (Senior) | Core API, database, business logic, auth, Stripe | 1 | Sprint 1–6 | Node.js, PostgreSQL, REST API, AWS, Stripe | In-house
Backend Developer (Mid) | Module APIs, data models, integrations support | 1 | Sprint 2–6 | Node.js, PostgreSQL, API development | In-house
UI/UX Designer | Screens, user flows, component library, mobile design | 1 | Sprint 1–4 | Figma, UI design, UX research, mobile design | In-house
QA / Tester | Sprint testing, bug reports, regression, security checks | 1 | Sprint 3–6 | Manual testing, API testing (Postman), bug tracking | In-house
Project Manager | Sprint planning, task tracking, team coordination, delivery | 1 | All sprints | Agile/Scrum, JIRA or equivalent, communication | In-house
⚙️ Recommended Tech Stack
Layer | Technology | Purpose
Frontend | React.js + Tailwind CSS | All web screens, dashboard, module UIs
Backend | Node.js + Express.js | API server, business logic, data processing
Database | AWS RDS — PostgreSQL | Primary database — scalable, managed, backed up
File Storage | AWS S3 | All documents, images, uploads — secure & scalable
Authentication | AWS Cognito | Login, signup, 2FA, session management
Email | AWS SES | All system emails — verification, alerts, reports
Payments | Stripe | Subscription billing, FPX, card, auto-renewal
Mobile | PWA (React) | Installable mobile app — same codebase as web
Hosting | AWS EC2 + CloudFront | Web server + global CDN for fast delivery
AI / OCR | AWS Textract + Bedrock | BQ scanning, OCR, AI auto-fill (Phase 2)
Notifications | AWS SES + Meta WhatsApp API | Email & WhatsApp alerts (WhatsApp in Phase 2)
Monitoring | AWS CloudWatch | Performance, error & security monitoring
CI/CD | GitHub Actions | Automated testing & deployment pipeline
Project Tracking | JIRA or Linear | Sprint planning, bug tracking, task management

## ✅ MVP Scope Per Module
ContractOS — MVP Scope Definition Per Module
Module | Basic (MVP) — What works at launch | Phase 2 — What comes after MVP | Sprint | Priority
Landing Page | Hero, Features, Pricing, Testimonials, FAQ, Contact, Footer Bilingual EN/BM Get Started CTA | Animations, live chat widget, blog section | Sprint 1 | 🔴 Critical
Login & Auth | Email/password login, signup, email verification Password reset Setup wizard | Social login (Google), optional 2FA, SSO | Sprint 1 | 🔴 Critical
Dashboard | Role-based views (13 roles) KPI cards, basic charts In-app notifications | Advanced analytics, custom widgets, AI insights | Sprint 2 | 🔴 Critical
User Management | Invite users, assign roles Deactivate accounts Basic permissions per role | Bulk import, advanced permission matrix | Sprint 2 | 🔴 Critical
Profiles | Create Subcon, Client, Supplier, Main Contractor profiles Auto-fill document headers Org hierarchy view | Profile verification, rating system | Sprint 2 | 🟠 High
Finance | Basic claim management (Progress & Full) Payment cert tracking Paid/Unpaid/Overdue/Partially Paid status | Retention tracking automation, advanced reporting | Sprint 3 | 🔴 Critical
Invoicing | Create & send invoices Multi-currency, SST/GST toggle Payment tracking Stripe subscription billing | Recurring invoices, bulk invoicing, accounting sync | Sprint 3 | 🔴 Critical
Projects | Create projects, assign team All 7 project statuses Milestones & deadlines Task assignment | AI Gantt, RFI auto-routing, project templates | Sprint 4 | 🔴 Critical
HR | Clock in/out with timestamp Leave apply & approve workflow Basic payroll (salary + OT) Attendance log | Biometric integration, advanced payroll, KPI tracking | Sprint 4 | 🟠 High
Tender/BQ | Create BQ, add line items, set quantities Basic version history Link to project | AI auto-fill, OCR scanning, market rate auto-pull | Sprint 5 | 🟠 High
Market Rates | Manual entry of material & labour rates Location selector per project | Live CIDB/KPKT API feed, auto-update rates | Sprint 5 | 🟡 Medium
Inventory | Add stock items, track quantities Low stock threshold alert Asset borrowing — manager approval | Auto purchase orders, supplier integration | Sprint 5 | 🟠 High
Document Manager | Upload, organise & download documents Basic drag & drop layout Auto-fill headers from profile | Digital signatures, version restore, approval workflow | Sprint 5 | 🟠 High
Settings | Session timeout config API key management Data export & backup Audit log (admin only) | Advanced security rules, PDPA deletion requests | Sprint 5 | 🟠 High
CRM | Add & manage leads Pipeline status view Convert lead to project | Full communication history, bid analytics | Sprint 6 | 🟡 Medium
Safety | Log incidents & near-misses Basic inspection checklist Staff cert expiry tracking | Full DOSH/OSHA compliance reports, HIRARC | Sprint 6 | 🟡 Medium
Fleet Management | Register vehicles & equipment Assign to project site Basic maintenance log | Fuel tracking, utilisation reports, cost tracking | Sprint 6 | 🟡 Medium
Mobile PWA | Installable on phone Dashboard, HR, Projects, Finance, Inventory accessible Works with internet | Full offline mode, push notifications, all modules | Sprint 6 | 🟠 High
RFI & Submittals | Basic RFI log per project Basic submittal log per project Status tracking | Auto-routing, response deadline alerts, reports | Sprint 6 | 🟡 Medium
Change Orders | Create change order Value-based approval workflow Link to project & finance | Budget auto-update, audit trail reports | Sprint 6 | 🟡 Medium
Notifications | In-app alerts Basic email alerts Fixed system notifications | WhatsApp API, user customisation, daily digest | Sprint 1–2 | 🟠 High
Reports | Basic PDF export per module Manual report generation | All formats (Word, Excel, CSV), scheduled auto-send | Sprint 6 | 🟡 Medium

## 🚩 Milestones & Risks
ContractOS — Milestones & Risk Register
🚩 Key Milestones
Target | Milestone | Description | Success Criteria | Status
Week 2 | Infrastructure live | AWS fully configured, CI/CD running, SSL active | URL resolves, HTTPS confirmed, deploy pipeline green | 🔲 Planned
Week 2 | Landing page published | Public-facing site live — bilingual EN/BM | All 8 sections visible, Get Started button works | 🔲 Planned
Week 4 | First login working | Users can sign up, verify email & access dashboard | End-to-end signup flow completed by test user | 🔲 Planned
Week 4 | Stripe billing live | Subscription tiers active — Free, Pro, Business, Enterprise | Test payment processed successfully via Stripe | 🔲 Planned
Week 6 | Finance module live | Invoice creation, sending & payment tracking working | Invoice created, sent, marked paid in full cycle | 🔲 Planned
Week 8 | Projects & HR live | Projects, milestones, clock in/out & leave working | PM creates project, staff clocks in via system | 🔲 Planned
Week 10 | BQ & Inventory live | BQ creation and inventory tracking working | BQ created with items, stock alert fires correctly | 🔲 Planned
Week 12 | All modules live | Every module has basic functionality working | All 22 modules accessible, no critical bugs | 🔲 Planned
Week 12 | MVP pilot launch | First real users onboarded to test the system | Minimum 3 pilot companies registered & active | 🔲 Planned
Week 12 | QA sign-off | Full QA pass — no P1 or P2 bugs remaining | QA checklist 100% complete, security review passed | 🔲 Planned
⚠️ Risk Register
Level | Risk | Impact | Mitigation | Sprint
🔴 High | Stripe FPX setup delays | Subscription billing blocked — users cannot pay | Start Stripe setup in Sprint 1, not Sprint 3 | Sprint 1
🔴 High | Payroll calculation errors | Legal liability if salaries calculated incorrectly | Validate with HR expert before Sprint 4 release | Sprint 4
🔴 High | WhatsApp Business API rejection | WhatsApp notifications unavailable at launch | Use email-only for MVP, WhatsApp in Phase 2 | Sprint 2
🔴 High | Team member unavailability | Sprint delays if key developer is absent | Document all code, no single point of failure | All sprints
🟠 Medium | Scope creep mid-sprint | Sprints overrun, MVP delayed beyond 3 months | Freeze scope per sprint, log extras for Phase 2 | All sprints
🟠 Medium | PDPA legal review delay | Launch blocked pending legal compliance sign-off | Engage legal advisor from Month 1 in parallel | Sprint 1
🟠 Medium | Document drag-and-drop complexity | Document Manager quality below expectation | Use proven library (react-dnd), timeboxed to 3 days | Sprint 5
🟠 Medium | AWS costs exceed budget | Infrastructure overrun before revenue | Set AWS billing alerts, use reserved instances | Sprint 1
🟡 Low | QA backlog in Sprint 6 | Bugs discovered too late, MVP delayed | QA runs from Sprint 3 onward, not just Sprint 6 | Sprint 3+
🟡 Low | Mobile PWA install issues on iOS | iOS users cannot install PWA correctly | Test on real iOS devices from Sprint 5 onward | Sprint 5

## 📜 Customer Policies
ContractOS — Customer-Facing Policies
📋 Policy 1 — Service Level Agreement (SLA)
Item | Tier | Commitment | Notes | Status
Uptime Guarantee | All tiers | 99.9% uptime — max ~8.7 hours downtime per year | Industry standard — matches AWS, Xero & HubSpot SLA | ✅ Defined
Penalty for Breach | All tiers | No penalty — best effort only at MVP stage | Upgrade to service credit system post-MVP when stable | ✅ Defined
Critical Issue Response | All tiers | 1 hour response time | System down — no access at all | ✅ Defined
Major Issue Response | All tiers | 4 hours response time | Core feature broken — e.g. Finance or HR unavailable | ✅ Defined
Minor Issue Response | All tiers | 24 hours response time | Non-critical bug — workaround exists | ✅ Defined
General Enquiry | All tiers | 48 hours response time | Feature questions, how-to support | ✅ Defined
Scheduled Maintenance | All tiers | Notified 48 hours in advance | Maintenance window outside business hours (MYT) | ✅ Defined
Disaster Recovery | All tiers | AWS automated daily backups — point-in-time recovery | RTO: 4 hours, RPO: 24 hours target | ✅ Defined
📋 Policy 2 — Terms of Service (ToS)
Item | Applies To | Clause Summary | Notes | Status
Governing Law | All tiers | Malaysian law (governed by Malaysian courts) | Enterprise tier: international arbitration option available | ✅ Defined
Liability Cap | All tiers | Capped at last 3 months of subscription paid | Standard MNC SaaS benchmark — Xero & QuickBooks model | ✅ Defined
Acceptable Use Policy | All tiers | Clearly listed banned uses | Illegal activity, reselling access, scraping, abuse of API, impersonation | ✅ Defined
Account Termination | All tiers | ContractOS reserves right to terminate for ToS violations | 30 days notice for non-breach terminations | ✅ Defined
Service Modifications | All tiers | ContractOS may modify features with 30 days notice | Enterprise: 60 days notice for major changes | ✅ Defined
Intellectual Property | All tiers | ContractOS owns platform IP — companies own their data | No transfer of ContractOS IP to users | ✅ Defined
Subscription & Billing | Paid tiers | Auto-renewal by default — user can disable | Governed by Stripe terms for payment processing | ✅ Defined
Dispute Resolution | All tiers | Malaysian courts — Enterprise: arbitration option | KLRCA (Kuala Lumpur Regional Centre for Arbitration) for Enterprise | ✅ Defined
📋 Policy 3 — Privacy Policy & Data Processor Obligations
Item | Position | Detail |  | Status
Data Processor Role | ContractOS = Data Processor | Companies own their data — ContractOS processes it on their behalf only |  | ✅ Defined
Data Controller Role | Companies = Data Controllers | Each company is responsible for lawful use of their data inside ContractOS |  | ✅ Defined
Data Export Right | Full export available anytime | Companies can request full export of all their data at any time |  | ✅ Defined
Data Deletion | After 7-year retention period | Data permanently deleted 7 years after account closure — PDPA & financial law compliant |  | ✅ Defined
Data Transfer Logging | Every external transfer logged | Timestamp, user & data summary logged per transfer — PDPA compliant |  | ✅ Defined
Third Party Disclosure | All third parties listed in policy | Stripe, AWS, WhatsApp API, accounting tools — all disclosed |  | ✅ Defined
Cross-Border Transfer | PDPA-equivalent standards | Overseas backup servers must meet PDPA-equivalent protection standards |  | ✅ Defined
Consent | At signup | Full consent notice shown — covers all data types collected |  | ✅ Defined
Breach Notification | Affected users notified immediately | Auto-detect breach, alert admin, notify affected companies promptly |  | ✅ Defined
Data Residency | Primary: Malaysia (AWS KL) | Backup: AWS global region — PDPA-equivalent standards enforced |  | ✅ Defined
📋 Policy 4 — Customisable Contract Clause Templates
Template | Type | Key Clauses Included | Customisable | Signable
Subcontractor Agreement | Project | Scope of work, payment terms, retention, liability, termination, dispute resolution | ✅ Yes | ✅ Digital
Letter of Award (LOA) | Project | Project details, contract sum, commencement date, completion date, special conditions | ✅ Yes | ✅ Digital
Non-Disclosure Agreement (NDA) | Legal | Confidential information definition, obligations, duration, exceptions, remedies | ✅ Yes | ✅ Digital
Performance Bond Agreement | Finance | Bond amount (5% default), bond type, conditions for call, release conditions, validity period | ✅ Yes | ✅ Digital
Board Resolution — Software Adoption | Governance | Resolution to adopt ContractOS, authorised signatories, effective date | ✅ Yes | ✅ Digital
Board Resolution — Signatory Authorisation | Governance | Authorised person, scope of authority, effective date, witness | ✅ Yes | ✅ Digital
Board Resolution — Director Appointment/Resignation | Governance | Director details, effective date, board acknowledgement | ✅ Yes | ✅ Digital
Board Resolution — Bank Account | Governance | Bank name, account purpose, authorised signatories, limits | ✅ Yes | ✅ Digital
⚠️ Legal Advisory: All policies and templates must be drafted and reviewed by a qualified Malaysian legal advisor before ContractOS goes live. These decisions form requirements — not final legal text.

## 🏛️ Governance & Docs
ContractOS — Governance & Documentation
📝 Employee NDAs & IP Assignment Agreements
Agreement Type | Signing Trigger | Key Provisions | Tracked In | Status
Employee NDA | At onboarding — before Day 1 | Non-disclosure of company info, client data, project details, trade secrets. Duration: during employment + 2 years after | HR Module | ✅ Defined
IP Assignment Agreement | At onboarding — before Day 1 | All work created during employment belongs to company. Covers designs, code, documents, processes & innovations | HR Module | ✅ Defined
Non-Compete Agreement | At onboarding — before Day 1 | Cannot join direct competitors during employment + 12 months after. Geographic & industry scope defined per role | HR Module | ✅ Defined
Confidentiality Agreement (Contractors) | Before project assignment | For freelancers & contractors — confidentiality of project scope, pricing, client details & methods | HR Module | ✅ Defined
🎓 Compliance Training Logs
Training Type | Frequency | What Is Tracked | Alert Trigger | Status
Safety Training (DOSH/OSHA) | Annual renewal | Completion date, trainer, cert number, expiry date per staff | 30 days before expiry — alert HR & Safety Officer | ✅ Defined
Data Privacy Training (PDPA) | Annual renewal | PDPA awareness completion, assessment score, date per staff | Annual reminder to HR — all staff must complete | ✅ Defined
Security Training | Annual renewal | Password policy, phishing awareness, data handling — completion per staff | Annual reminder — alert HR if not completed within 30 days | ✅ Defined
HR & Workplace Compliance | At onboarding + annual | Anti-harassment, code of conduct, disciplinary policy — acknowledgement per staff | At onboarding trigger + annual renewal alert to HR | ✅ Defined
🔐 ISO 27001 & SOC 2 Alignment Documentation
Control Area | Standard | ContractOS Implementation | Evidence Required | Status
Access Control | ISO 27001 / SOC 2 | Role-based access — 13 roles, strict permissions per module | Access control matrix, role assignment logs | ✅ Self-Assessed
Encryption | ISO 27001 / SOC 2 | HTTPS/SSL in transit + server-side encryption at rest (AWS) | SSL cert screenshot, AWS encryption config | ✅ Self-Assessed
Audit Logging | ISO 27001 / SOC 2 | Full log of every user action — admin access only | Sample audit log export, retention policy doc | ✅ Self-Assessed
Data Transfer Logging | ISO 27001 / SOC 2 / PDPA | Every external data transfer logged — timestamp, user, summary | Transfer log sample, AWS Step Functions execution log | ✅ Self-Assessed
Incident Response | ISO 27001 | Auto-detect breach, alert admin, notify affected users | Incident response procedure doc, test drill record | ✅ Self-Assessed
Business Continuity | ISO 27001 / SOC 2 | AWS daily backups, multi-region failover, 99.9% SLA | AWS backup config, RTO/RPO documentation | ✅ Self-Assessed
Vendor Management | ISO 27001 | All third parties listed — Stripe, AWS, WhatsApp, DocuSign | Vendor register, third-party risk assessments | ✅ Self-Assessed
Security Training | ISO 27001 | Annual security training for all staff — tracked in compliance log | Training completion report per staff | ✅ Self-Assessed
Vulnerability Management | ISO 27001 / SOC 2 | Pen testing before launch, monthly AWS CloudWatch review | Pen test report, vulnerability scan results | ✅ Self-Assessed
Data Retention & Disposal | ISO 27001 / PDPA | 7-year retention, secure deletion after period ends | Data retention policy doc, deletion procedure | ✅ Self-Assessed
Change Management | ISO 27001 | All system changes via GitHub Actions CI/CD with approval gates | CI/CD pipeline config, change log records | ✅ Self-Assessed
Certification Status | ISO 27001 / SOC 2 | Self-assessed alignment — formal certification planned post-MVP | Self-assessment checklist, gap analysis report | ✅ Self-Assessed

## ⚡ Integration Architecture
ContractOS — Integration Architecture (AWS Step Functions)
⚡ API Automation Engine — AWS Step Functions
Workflow | Trigger | Steps / Actions | External System | Status
Invoice Sync to Accounting | Invoice marked as Sent in ContractOS | 1. Extract invoice data 2. Map fields to accounting format 3. POST to QuickBooks/SQL/Xero API 4. Log transfer with timestamp & user 5. Update sync status in ContractOS | QuickBooks / SQL / Xero | 🔲 Planned
Payment Certificate Alert | Payment cert not closed after 30 days | 1. Detect overdue cert 2. Build alert payload 3. Send email via AWS SES 4. Send WhatsApp via Meta API 5. Log alert in audit trail | AWS SES + WhatsApp API | 🔲 Planned
DocuSign Signing Workflow | Document marked Ready for Signing | 1. Prepare document envelope 2. Send to DocuSign API 3. Monitor signing status 4. Retrieve signed doc when complete 5. Store in Document Manager + log transfer | DocuSign / MyEG | 🔲 Planned
Calendar Sync — Milestones | Project milestone created or updated | 1. Extract milestone data 2. Format to calendar event 3. POST to Google/Outlook Calendar API 4. Handle conflicts 5. Log sync result | Google Calendar / Outlook | 🔲 Planned
WhatsApp Notification | Critical system alert triggered | 1. Detect alert event 2. Build WhatsApp message payload 3. POST to Meta WhatsApp Business API 4. Handle delivery receipt 5. Log notification in audit trail | Meta WhatsApp Business API | 🔲 Planned
Safety Cert Renewal Alert | Cert expiry within 30 days detected | 1. Scan safety cert expiry dates 2. Build reminder payload per staff 3. Send email + in-app alert 4. Log alert timestamp & recipient 5. Repeat weekly until renewed | AWS SES + In-app | 🔲 Planned
Subcon Claim Approval Flow | Subcon submits claim via portal | 1. Receive claim submission 2. Route to main contractor Finance module 3. Notify Finance via email + in-app 4. Await approval action 5. Update claim status + notify subcon | Internal ContractOS | 🔲 Planned
Scheduled Report Delivery | Report schedule trigger fires | 1. Generate report data 2. Build PDF/Excel file 3. Attach to email 4. Send via AWS SES to recipients 5. Log delivery in audit trail | AWS SES + AWS S3 | 🔲 Planned
🗺️ Data Mapping Interface — Admin Configuration
ContractOS Field | External System | Mapped To | Admin Editable | Status
Invoice Number | QuickBooks | Invoice → DocNumber | ✅ Yes | 🔲 Phase 2
Invoice Amount | QuickBooks | Invoice → TotalAmt | ✅ Yes | 🔲 Phase 2
Client Name | QuickBooks / SQL Account | Customer → DisplayName | ✅ Yes | 🔲 Phase 2
Invoice Date | Xero | Invoice → Date | ✅ Yes | 🔲 Phase 2
Payment Status | SQL Account | Invoice → Status (Paid/Unpaid) | ✅ Yes | 🔲 Phase 2
Project Code | QuickBooks | Invoice → CustomField → ProjectRef | ✅ Yes | 🔲 Phase 2
Staff Name | Payroll System | Employee → FullName | ✅ Yes | 🔲 Phase 2
Document ID | DocuSign | Envelope → ClientUserId | ✅ Yes | 🔲 Phase 2

## 🤝 Subcontractor Module
ContractOS — Subcontractor Portal Module
Subcontractors log into the main contractor's ContractOS system with strictly limited, segregated access — not a separate login or workspace.
🏗️ Subcontractor Capabilities & Access Rights
Feature | Access Level | Description | Approval Required | Status
View Assigned Scope & BQ | View only | Subcon sees only their assigned BQ items & scope — not other subcons or full project BQ | No | ✅ Defined
Submit Progress Updates | Submit | Log daily progress against assigned scope — auto-updates main contractor project dashboard | No — automatic | ✅ Defined
Submit Site Diary Entries | Submit | Record daily site activities, workforce & equipment used for their scope | No — automatic | ✅ Defined
Submit Claims & Invoices | Submit | Submit progress or full claims to main contractor for approval & payment processing | Yes — Finance team | ✅ Defined
View Own Claim Status | View only | See status of submitted claims: Pending, Approved, Paid, Rejected | No | ✅ Defined
View Payment Status | View only | See payment status for approved claims only — not other subcon financials | No | ✅ Defined
View & Acknowledge RFIs | View + acknowledge | Receive RFIs from main contractor, acknowledge receipt & provide responses | No | ✅ Defined
View Site Instructions | View + acknowledge | Receive & acknowledge site instructions issued by main contractor or PM | No | ✅ Defined
View Upcoming Deadlines | View only | See milestone dates & deadlines relevant to their assigned scope only | No | ✅ Defined
Upload Supporting Documents | Submit | Upload delivery orders, test reports & scope completion evidence | No — automatic | ✅ Defined
Dashboard | View only | Dedicated subcon dashboard: scope completion %, pending claims, upcoming deadlines | No | ✅ Defined
Mobile PWA Access | Full mobile | Full subcon portal accessible on mobile — submit progress & docs from site | No | ✅ Defined
Notifications | Receive only | Receive alerts for new instructions, RFI responses, claim approvals & payment updates | No | ✅ Defined
🔒 Data Segregation Rules
Rule | Applies To | How It Works |  | Status
Scope isolation | All subcons | Subcon A sees only their scope — never Subcon B's scope, rates or BQ items |  | ✅ Defined
Subcon-to-subcon blind | All subcons | No subcon can see which other subcontractors are on the same project |  | ✅ Defined
Financial isolation | All subcons | Subcon sees own claims & payment status only — never overall project financials |  | ✅ Defined
Document isolation | All subcons | Subcon sees only documents shared with them — not contractor's internal docs |  | ✅ Defined
Staff isolation | All subcons | Subcon cannot see contractor's staff list, HR data or internal communications |  | ✅ Defined
Access auto-expiry | All subcons | Access automatically revoked when assigned project scope is marked complete |  | ✅ Defined
Manual revocation | All subcons | Main contractor admin can revoke subcon access at any time instantly |  | ✅ Defined
Audit trail | All subcons | Every subcon action logged — what they viewed, submitted or uploaded & when |  | ✅ Defined
🔄 Subcontractor ↔ Main Contractor Integration Flow
Step | Actor | Action | System Response | Status
1 | Main Contractor | Assigns BQ scope to subcontractor in project | Subcon gets notified, scope appears in their dashboard | ✅ Defined
2 | Subcontractor | Logs in, views assigned scope & deadlines | Dashboard shows scope completion %, upcoming milestones | ✅ Defined
3 | Main Contractor | Sends RFI or site instruction to subcon | Subcon receives in-app + email/WhatsApp notification | ✅ Defined
4 | Subcontractor | Acknowledges RFI & submits response | Main contractor PM notified, RFI log updated | ✅ Defined
5 | Subcontractor | Submits daily progress update | Auto-updates main project dashboard progress % instantly | ✅ Defined
6 | Subcontractor | Uploads delivery orders & test reports | Documents saved, PM & QS notified of new uploads | ✅ Defined
7 | Subcontractor | Submits progress claim for completed work | Claim auto-appears in Finance module — Finance team alerted | ✅ Defined
8 | Main Contractor | Finance team reviews & approves claim | Subcon notified of approval, payment status updated | ✅ Defined
9 | Main Contractor | Marks subcon scope as complete | Subcon access auto-expires, final docs archived | ✅ Defined
10 | System | Access expiry confirmed | Audit log entry created, subcon can no longer log in | ✅ Defined